## Review Guide
Nimbus Release Acceptance Test | Version 2
Purpose | Review and execute customer-visible release acceptance checks.
Smoke | 26 CRITICAL checks for fast deployment confidence.
Release | 63 CRITICAL and HIGH checks for a normal release.
Full Regression | All 128 in-scope checks.
Results | Pass, Fail, Blocked, or Not Run. Add a note for every failure.
Known issue | T-09 currently fails: contact details return as one combined line after reload.
Review note | Confirm priorities, wording, prerequisites, and expected results before using this workbook for sign-off.

## Smoke
Block | ID | What we are testing | Before you start | What to do | What you should see | Priority | Tester | Date | Result | Notes
SIGN IN (`/login`) | T-01 | Sign in with email and password | You have an account and its password. | 1. Open the portal. 2. Enter your email and password. 3. Press Sign in. | The password step is accepted and the screen asks for a code. | CRITICAL |  |  | Not Run
SIGN IN (`/login`) | T-02 | The code arrives and signs you in | You are on the code step from T-01. | 1. Read the code that was sent to you. 2. Enter it. 3. Press Verify. | You land on the dashboard, signed in, with your name shown. | CRITICAL |  |  | Not Run
SIGN IN (`/login`) | T-08 | Sign out | You are signed in. | 1. Press Sign out. 2. Press the browser Back button. | You are returned to the sign-in screen and Back does not get you in. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-11 | Permissions decide the menu | The account from T-10, with only Calls allowed. | 1. Edit its permissions to Calls only. 2. Sign in as that account. | Only the screens it is allowed appear; the rest are not reachable, including by typing the address. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-17 | One customer cannot see another | needs: a second customer on the same system. | 1. Sign in as an account of customer A. 2. Open the accounts list. | Only customer A's accounts are listed. Nothing of customer B appears anywhere. | CRITICAL |  |  | Not Run
APPLICATIONS (`/environments`) | T-23 | Create an application | You have full access. | 1. Create an application with a name and a domain. 2. Save. | It appears in the list and can be picked in the environment selector. | CRITICAL |  |  | Not Run
USERS (`/users`) | T-28 | Create a user | An application exists. | 1. Press Create User. 2. Fill in name, email and extension number. 3. Save. 4. Open Devices. | The user is listed AND a device for them appears on Devices. | CRITICAL |  |  | Not Run
USERS (`/users`) | T-29 | The new user's phone can register | The user from T-28. needs: a softphone. | 1. Configure the softphone with that extension and its password. 2. Register it. 3. Open Devices. | The phone registers and the device shows as online. | CRITICAL |  |  | Not Run | A device that exists but was never sent to its node looks fine here and refuses every registration — this row is what catches that.
USERS (`/users`) | T-30 | The user can sign in to the portal | The user from T-28. | 1. Sign in at the user portal with their email and password. | They reach their own screens (My calls, Phone) and see only their own calls. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-34 | Create a device | An application exists. | 1. Press Add Device. 2. Fill in Name, Device Number and SIP Password. 3. Save. | It appears in the list straight away. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-35 | The device registers | The device from T-34. needs: a softphone. | 1. Point the softphone at the platform with that number and password. 2. Register. 3. Reload the list. | The device shows as registered / online. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-36 | Call between two devices | Two registered devices. needs: two softphones. | 1. From device A, dial device B's number. | B rings, the call connects, both sides have audio, and hanging up ends it on both. | CRITICAL |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-43 | Add a number | An application exists. | 1. Press Add DID. 2. Enter the number and save. | It is listed against that application. | CRITICAL |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-44 | A number rings a device | The number from T-43 and a registered device. needs: a way to dial the number. | 1. Point the number at that device. 2. Call the number from outside. | The device rings, the call connects with audio both ways. | CRITICAL |  |  | Not Run
PROVIDERS (`/providers`) | T-61 | Outbound call through the provider | The provider from T-60, a registered device. needs: a number you can call. | 1. Point outbound calls at the provider. 2. From the device, dial an outside number. | The far end rings, the call connects with audio, and it appears in Calls as outgoing. | CRITICAL |  |  | Not Run
PROVIDERS (`/providers`) | T-62 | Inbound from the provider | A number delivered by that provider. | 1. Call that number from outside. | The call arrives and follows the routing set for the number. | CRITICAL |  |  | Not Run
NODES (`/nodes`) | T-65 | Which nodes are connected | You are signed in as root. | 1. Open Nodes. | Every node is listed with an up-to-date connected state, and the ones that are actually running show as connected. | CRITICAL |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-73 | The finished call is in the log | The call from T-71, hung up. | 1. Open the call log. | The call is there with the right numbers, direction, start time and duration. | CRITICAL |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-79 | An agent sees only their own calls | A user with the portal. | 1. Sign in as the user. 2. Open My calls. | They see their own calls, and none of anyone else's. | CRITICAL |  |  | Not Run
SERVICES (`/services`) | T-86 | The webhook is delivered | The service from T-85. **Wait one minute after saving.** | 1. Send it a test event with delivery turned on. 2. Look at your URL. 3. Open the service. | Your URL received the request, and the service's sent counter went up. | CRITICAL |  |  | Not Run | The screen reports that the event was *sent*, not that your endpoint accepted it — check your own endpoint and the counter. Changes take up to a minute to take effect; judging sooner makes a correct fix look broken.
SUBSCRIPTIONS, TARIFFS AND BILLING | T-95 | Calls use the balance | A subscription with a small balance. needs: a chargeable call. | 1. Note the balance. 2. Make a chargeable call. 3. Reload. | The balance has gone down and the call is in Transactions with a cost. | CRITICAL |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-110 | Dashboard figures | Some calls today. | 1. Open the dashboard. 2. Compare with the call log for the same period. | The totals agree with the call log. | CRITICAL |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-111 | Live updates while a call runs | A registered device. | 1. Open the live screen. 2. Make a call and hang up. | The call appears while it runs and the counts go back down after it ends, without reloading. | CRITICAL |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-114 | System health | You are signed in. | 1. Open the health screen. | Every check is listed and the essential ones are green. | CRITICAL |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-124 | One customer's logs only | needs: a second customer. | 1. Sign in as customer A. 2. Search Logs for something of customer B's. | Nothing of customer B's is returned. | CRITICAL |  |  | Not Run
THE WHOLE WAY THROUGH — run this last | T-130 | A new customer, end to end | You are signed in with full access. needs: two softphones and a number. | 1. Create an application. 2. Create two users on it. 3. Register both softphones. 4. Add a number and point it at one of them. 5. Call between the two devices. 6. Call the number from outside. 7. Open the call log, the dashboard and Transactions. | Every step works without a developer touching anything, and the calls you made are the calls the log, the dashboard and the charges show. | CRITICAL |  |  | Not Run | If this row passes, the release is usable. If it fails, the release is not, whatever else passed.

## Release
Block | ID | What we are testing | Before you start | What to do | What you should see | Priority | Tester | Date | Result | Notes
SIGN IN (`/login`) | T-01 | Sign in with email and password | You have an account and its password. | 1. Open the portal. 2. Enter your email and password. 3. Press Sign in. | The password step is accepted and the screen asks for a code. | CRITICAL |  |  | Not Run
SIGN IN (`/login`) | T-02 | The code arrives and signs you in | You are on the code step from T-01. | 1. Read the code that was sent to you. 2. Enter it. 3. Press Verify. | You land on the dashboard, signed in, with your name shown. | CRITICAL |  |  | Not Run
SIGN IN (`/login`) | T-03 | A wrong code is refused | You are on the code step. | 1. Enter a code that is not the one you were sent. 2. Press Verify. | You are told the code is wrong and you stay signed out. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-04 | A code cannot be used twice | You have signed in once with a code (T-02). | 1. Sign out. 2. Sign in again with the same email and password. 3. Enter the PREVIOUS code. | The old code is refused; only the new one works. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-05 | Wrong password | You know the account's real password. | 1. Enter the right email with a wrong password. 2. Press Sign in. | You are told the details are wrong. No code is sent. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-06 | Forgotten password | You can read the mail for this account. | 1. Press Forgot password. 2. Enter your email. 3. Follow the mail and set a new password. 4. Sign in with the new password. | The new password works and the old one no longer does. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-08 | Sign out | You are signed in. | 1. Press Sign out. 2. Press the browser Back button. | You are returned to the sign-in screen and Back does not get you in. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-10 | Create an account | You have full access. | 1. Press Create New. 2. Fill in a name, an email and permissions. 3. Save. 4. Sign in as that account in another browser profile. | The account appears in the list and can sign in. | HIGH |  |  | Not Run
ACCOUNTS (`/accounts`) | T-11 | Permissions decide the menu | The account from T-10, with only Calls allowed. | 1. Edit its permissions to Calls only. 2. Sign in as that account. | Only the screens it is allowed appear; the rest are not reachable, including by typing the address. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-12 | Read-only permission | An account with read-only rights on a screen. | 1. Sign in as it. 2. Open that screen and try to save a change. | The screen opens, the save is refused, nothing changes. | HIGH |  |  | Not Run
ACCOUNTS (`/accounts`) | T-15 | Disable an account | The account from T-10. | 1. Switch it off. 2. Try to sign in as it. | It cannot sign in while disabled, and can again once re-enabled. | HIGH |  |  | Not Run
ACCOUNTS (`/accounts`) | T-17 | One customer cannot see another | needs: a second customer on the same system. | 1. Sign in as an account of customer A. 2. Open the accounts list. | Only customer A's accounts are listed. Nothing of customer B appears anywhere. | CRITICAL |  |  | Not Run
MY ACCOUNT AND CUSTOMER (`/account`) | T-21 | Switching customer | needs: an account with more than one customer. | 1. Use the customer switcher. 2. Open Devices and Calls. | Every screen now shows the other customer's data, and nothing of the first. | HIGH |  |  | Not Run
APPLICATIONS (`/environments`) | T-23 | Create an application | You have full access. | 1. Create an application with a name and a domain. 2. Save. | It appears in the list and can be picked in the environment selector. | CRITICAL |  |  | Not Run
APPLICATIONS (`/environments`) | T-25 | Give an account access to it | The application from T-23 and a second account. | 1. Add the application to that account. 2. Sign in as that account. | The account can now pick that application and see its data. | HIGH |  |  | Not Run
APPLICATIONS (`/environments`) | T-26 | Delete an application | An application with at least one device, one user and one number on it. | 1. Note what is on it. 2. Delete it. 3. Open Devices, Users and Routing. | The application is gone AND everything that belonged to it is gone too — no leftover devices, users or numbers. | HIGH |  |  | Not Run | The point of this row is the leftovers, not the application.
USERS (`/users`) | T-28 | Create a user | An application exists. | 1. Press Create User. 2. Fill in name, email and extension number. 3. Save. 4. Open Devices. | The user is listed AND a device for them appears on Devices. | CRITICAL |  |  | Not Run
USERS (`/users`) | T-29 | The new user's phone can register | The user from T-28. needs: a softphone. | 1. Configure the softphone with that extension and its password. 2. Register it. 3. Open Devices. | The phone registers and the device shows as online. | CRITICAL |  |  | Not Run | A device that exists but was never sent to its node looks fine here and refuses every registration — this row is what catches that.
USERS (`/users`) | T-30 | The user can sign in to the portal | The user from T-28. | 1. Sign in at the user portal with their email and password. | They reach their own screens (My calls, Phone) and see only their own calls. | CRITICAL |  |  | Not Run
USERS (`/users`) | T-33 | Delete a user | The user from T-28. | 1. Delete them. 2. Open Devices. 3. Try to register their softphone. | The user and their device are gone and the phone can no longer register. | HIGH |  |  | Not Run
DEVICES (`/extensions`) | T-34 | Create a device | An application exists. | 1. Press Add Device. 2. Fill in Name, Device Number and SIP Password. 3. Save. | It appears in the list straight away. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-35 | The device registers | The device from T-34. needs: a softphone. | 1. Point the softphone at the platform with that number and password. 2. Register. 3. Reload the list. | The device shows as registered / online. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-36 | Call between two devices | Two registered devices. needs: two softphones. | 1. From device A, dial device B's number. | B rings, the call connects, both sides have audio, and hanging up ends it on both. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-37 | Wrong password is refused | The device from T-34. | 1. Set the wrong SIP password on the softphone. 2. Register. | Registration is refused and the device stays offline. | HIGH |  |  | Not Run
DEVICES (`/extensions`) | T-42 | Delete a device | The device from T-34. | 1. Delete it. 2. Try to register its softphone. | It is gone from the list and can no longer register. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-43 | Add a number | An application exists. | 1. Press Add DID. 2. Enter the number and save. | It is listed against that application. | CRITICAL |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-44 | A number rings a device | The number from T-43 and a registered device. needs: a way to dial the number. | 1. Point the number at that device. 2. Call the number from outside. | The device rings, the call connects with audio both ways. | CRITICAL |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-45 | A number goes to an IVR | An IVR with at least one option. | 1. Point the number at the IVR. 2. Call it. 3. Press the option. | You hear the menu and the key press takes you where the option says. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-46 | A number goes to a queue | A queue with an agent logged in. | 1. Point the number at the queue. 2. Call it. | You hear the queue treatment and the agent's phone rings. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-50 | Delete a number | The number from T-43. | 1. Delete it. 2. Call it. | It is gone from the list and the call is not answered by the platform. | HIGH |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-52 | Create a queue | A device to act as agent. | 1. Press Create Queue. 2. Add the device as an agent. 3. Save. | The queue is listed with its agent. | HIGH |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-53 | A queue call reaches the agent | The queue from T-52, agent registered. | 1. Call into the queue. | The agent's phone rings; answering connects the caller; the call appears in Calls. | HIGH |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-55 | Create an IVR | An announcement to play. | 1. Press Create IVR. 2. Add a greeting and at least one key option. 3. Save. | The IVR is listed with its options. | HIGH |  |  | Not Run
PROVIDERS (`/providers`) | T-60 | Add a provider | needs: carrier details. | 1. Press Add Provider. 2. Fill in the details and save. | It is listed. | HIGH |  |  | Not Run
PROVIDERS (`/providers`) | T-61 | Outbound call through the provider | The provider from T-60, a registered device. needs: a number you can call. | 1. Point outbound calls at the provider. 2. From the device, dial an outside number. | The far end rings, the call connects with audio, and it appears in Calls as outgoing. | CRITICAL |  |  | Not Run
PROVIDERS (`/providers`) | T-62 | Inbound from the provider | A number delivered by that provider. | 1. Call that number from outside. | The call arrives and follows the routing set for the number. | CRITICAL |  |  | Not Run
NODES (`/nodes`) | T-65 | Which nodes are connected | You are signed in as root. | 1. Open Nodes. | Every node is listed with an up-to-date connected state, and the ones that are actually running show as connected. | CRITICAL |  |  | Not Run
NODES (`/nodes`) | T-66 | A node that is off shows as off | needs: a node you can stop. | 1. Stop the node. 2. Reload Nodes. | It shows as not connected within a few seconds, with a reason. | HIGH |  |  | Not Run
NODES (`/nodes`) | T-70 | Only root sees Nodes | An account without node rights. | 1. Sign in as it. 2. Look for Nodes, then type the address directly. | The screen is neither listed nor reachable. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-71 | Start a call from the screen | A registered device. | 1. Start a call to that device from Calls. 2. Answer it. | The device rings, the call connects, and it appears in the live list while it runs. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-72 | A call in progress is shown | A call running. | 1. Watch the Calls screen while the call is up. | The call is listed with both parties and a running duration, and disappears when it ends. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-73 | The finished call is in the log | The call from T-71, hung up. | 1. Open the call log. | The call is there with the right numbers, direction, start time and duration. | CRITICAL |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-74 | End a call from the screen | A call running. | 1. Press hang up on that call. | Both phones drop within a second or two and the call leaves the live list. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-79 | An agent sees only their own calls | A user with the portal. | 1. Sign in as the user. 2. Open My calls. | They see their own calls, and none of anyone else's. | CRITICAL |  |  | Not Run
SERVICES (`/services`) | T-85 | Create a webhook | needs: a URL you can watch (any request-catching site). | 1. Press New Service. 2. Choose webhook, paste the URL, pick when it should fire and which applications it covers. 3. Save. | It is listed as enabled. | HIGH |  |  | Not Run
SERVICES (`/services`) | T-86 | The webhook is delivered | The service from T-85. **Wait one minute after saving.** | 1. Send it a test event with delivery turned on. 2. Look at your URL. 3. Open the service. | Your URL received the request, and the service's sent counter went up. | CRITICAL |  |  | Not Run | The screen reports that the event was *sent*, not that your endpoint accepted it — check your own endpoint and the counter. Changes take up to a minute to take effect; judging sooner makes a correct fix look broken.
SERVICES (`/services`) | T-87 | A real call fires it | The service from T-85, set to fire at end of call. | 1. Make and end a call on a covered application. 2. Look at your URL. | The request arrives for the real call, with that call's details. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-92 | Add a subscription | An application. | 1. Press Add Subscription. 2. Pick the plan and dates. 3. Save. | It is listed against the application with its dates. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-94 | Add balance | The subscription from T-92. | 1. Press Add Balance and add an amount. | The balance goes up by that amount and a transaction is recorded. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-95 | Calls use the balance | A subscription with a small balance. needs: a chargeable call. | 1. Note the balance. 2. Make a chargeable call. 3. Reload. | The balance has gone down and the call is in Transactions with a cost. | CRITICAL |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-96 | No balance, no call | A subscription with no balance. | 1. Try a chargeable call. | The call is refused, and the reason is visible in Logs. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-97 | End a subscription | The subscription from T-92. | 1. Terminate it. 2. Try a chargeable call. | It shows as ended and chargeable calls stop working. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-98 | Create a tariff | You have full access. | 1. Press Create Tariff. 2. Add rates for a few prefixes, including one long and one short. | The tariff is listed with its rates. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-99 | What a number costs | The tariff from T-98, with rates for `1` and `1212`. | 1. Ask the tariff for the rate for a +1 212 number. | The more specific rate (`1212`) is the one quoted, not `1`. | HIGH |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-110 | Dashboard figures | Some calls today. | 1. Open the dashboard. 2. Compare with the call log for the same period. | The totals agree with the call log. | CRITICAL |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-111 | Live updates while a call runs | A registered device. | 1. Open the live screen. 2. Make a call and hang up. | The call appears while it runs and the counts go back down after it ends, without reloading. | CRITICAL |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-114 | System health | You are signed in. | 1. Open the health screen. | Every check is listed and the essential ones are green. | CRITICAL |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-115 | A stopped service shows red | needs: a service you can stop. | 1. Stop it. 2. Reload health. | It goes red and names what is wrong. | HIGH |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-118 | Recent activity in Logs | Anything done in the last few minutes. | 1. Open Logs. | Recent lines are there, newest first, with times that make sense. | HIGH |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-119 | Find a line | A call you just made. | 1. Search Logs for its number or reference. | The lines for that call are found. | HIGH |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-124 | One customer's logs only | needs: a second customer. | 1. Sign in as customer A. 2. Search Logs for something of customer B's. | Nothing of customer B's is returned. | CRITICAL |  |  | Not Run
REPORTS AND NOTIFICATIONS | T-125 | Run a report | Some calls in the period. | 1. Open Reports, pick a period, run one. | The figures agree with the call log for that period. | HIGH |  |  | Not Run
THE WHOLE WAY THROUGH — run this last | T-130 | A new customer, end to end | You are signed in with full access. needs: two softphones and a number. | 1. Create an application. 2. Create two users on it. 3. Register both softphones. 4. Add a number and point it at one of them. 5. Call between the two devices. 6. Call the number from outside. 7. Open the call log, the dashboard and Transactions. | Every step works without a developer touching anything, and the calls you made are the calls the log, the dashboard and the charges show. | CRITICAL |  |  | Not Run | If this row passes, the release is usable. If it fails, the release is not, whatever else passed.

## Full Regression
Block | ID | What we are testing | Before you start | What to do | What you should see | Priority | Tester | Date | Result | Notes
SIGN IN (`/login`) | T-01 | Sign in with email and password | You have an account and its password. | 1. Open the portal. 2. Enter your email and password. 3. Press Sign in. | The password step is accepted and the screen asks for a code. | CRITICAL |  |  | Not Run
SIGN IN (`/login`) | T-02 | The code arrives and signs you in | You are on the code step from T-01. | 1. Read the code that was sent to you. 2. Enter it. 3. Press Verify. | You land on the dashboard, signed in, with your name shown. | CRITICAL |  |  | Not Run
SIGN IN (`/login`) | T-03 | A wrong code is refused | You are on the code step. | 1. Enter a code that is not the one you were sent. 2. Press Verify. | You are told the code is wrong and you stay signed out. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-04 | A code cannot be used twice | You have signed in once with a code (T-02). | 1. Sign out. 2. Sign in again with the same email and password. 3. Enter the PREVIOUS code. | The old code is refused; only the new one works. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-05 | Wrong password | You know the account's real password. | 1. Enter the right email with a wrong password. 2. Press Sign in. | You are told the details are wrong. No code is sent. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-06 | Forgotten password | You can read the mail for this account. | 1. Press Forgot password. 2. Enter your email. 3. Follow the mail and set a new password. 4. Sign in with the new password. | The new password works and the old one no longer does. | HIGH |  |  | Not Run
SIGN IN (`/login`) | T-07 | Staying signed in | You are signed in. | 1. Reload the page. 2. Open another screen. | You stay signed in; you are not asked for the code again. | MEDIUM |  |  | Not Run
SIGN IN (`/login`) | T-08 | Sign out | You are signed in. | 1. Press Sign out. 2. Press the browser Back button. | You are returned to the sign-in screen and Back does not get you in. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-09 | Account details | You have full access. | 1. Open the account details. 2. Change a contact detail and save. 3. Reload the page. | The change is saved and shown after reloading. | MEDIUM |  |  | Not Run | See known issues — this currently fails.
ACCOUNTS (`/accounts`) | T-10 | Create an account | You have full access. | 1. Press Create New. 2. Fill in a name, an email and permissions. 3. Save. 4. Sign in as that account in another browser profile. | The account appears in the list and can sign in. | HIGH |  |  | Not Run
ACCOUNTS (`/accounts`) | T-11 | Permissions decide the menu | The account from T-10, with only Calls allowed. | 1. Edit its permissions to Calls only. 2. Sign in as that account. | Only the screens it is allowed appear; the rest are not reachable, including by typing the address. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-12 | Read-only permission | An account with read-only rights on a screen. | 1. Sign in as it. 2. Open that screen and try to save a change. | The screen opens, the save is refused, nothing changes. | HIGH |  |  | Not Run
ACCOUNTS (`/accounts`) | T-13 | Reset an account password | The account from T-10. | 1. Open it. 2. Press Reset Password. 3. Sign in with the new password. | The new password works; the old one does not. | MEDIUM |  |  | Not Run
ACCOUNTS (`/accounts`) | T-14 | API token for an account | You have full access. | 1. Open an account. 2. Press Generate Basic Auth Token. 3. Note it. | A token is shown and can be copied. | LOW |  |  | Not Run
ACCOUNTS (`/accounts`) | T-15 | Disable an account | The account from T-10. | 1. Switch it off. 2. Try to sign in as it. | It cannot sign in while disabled, and can again once re-enabled. | HIGH |  |  | Not Run
ACCOUNTS (`/accounts`) | T-16 | Delete an account | The account from T-10. | 1. Delete it. 2. Reload the list. 3. Try to sign in as it. | It is gone from the list and cannot sign in. | MEDIUM |  |  | Not Run
ACCOUNTS (`/accounts`) | T-17 | One customer cannot see another | needs: a second customer on the same system. | 1. Sign in as an account of customer A. 2. Open the accounts list. | Only customer A's accounts are listed. Nothing of customer B appears anywhere. | CRITICAL |  |  | Not Run
ACCOUNTS (`/accounts`) | T-18 | Finding an account | More than a page of accounts. | 1. Search for one by name or email. 2. Page through the list. | The search finds it and paging does not lose or repeat rows. | LOW |  |  | Not Run
MY ACCOUNT AND CUSTOMER (`/account`) | T-19 | Your own profile | You are signed in. | 1. Open your account. 2. Change your display name and save. 3. Reload. | The new name is kept and is shown in the top bar. | MEDIUM |  |  | Not Run
MY ACCOUNT AND CUSTOMER (`/account`) | T-20 | Company details | You have full access. | 1. Open the customer details. 2. Change the company contact details and save. 3. Reload. | The change is kept. | MEDIUM |  |  | Not Run
MY ACCOUNT AND CUSTOMER (`/account`) | T-21 | Switching customer | needs: an account with more than one customer. | 1. Use the customer switcher. 2. Open Devices and Calls. | Every screen now shows the other customer's data, and nothing of the first. | HIGH |  |  | Not Run
MY ACCOUNT AND CUSTOMER (`/account`) | T-22 | Changing your password | You know your current password. | 1. Change your password. 2. Sign out and back in. | Only the new password works. | MEDIUM |  |  | Not Run
APPLICATIONS (`/environments`) | T-23 | Create an application | You have full access. | 1. Create an application with a name and a domain. 2. Save. | It appears in the list and can be picked in the environment selector. | CRITICAL |  |  | Not Run
APPLICATIONS (`/environments`) | T-24 | Edit an application | The application from T-23. | 1. Change its name and save. 2. Reload. | The new name shows everywhere it is listed. | MEDIUM |  |  | Not Run
APPLICATIONS (`/environments`) | T-25 | Give an account access to it | The application from T-23 and a second account. | 1. Add the application to that account. 2. Sign in as that account. | The account can now pick that application and see its data. | HIGH |  |  | Not Run
APPLICATIONS (`/environments`) | T-26 | Delete an application | An application with at least one device, one user and one number on it. | 1. Note what is on it. 2. Delete it. 3. Open Devices, Users and Routing. | The application is gone AND everything that belonged to it is gone too — no leftover devices, users or numbers. | HIGH |  |  | Not Run | The point of this row is the leftovers, not the application.
APPLICATIONS (`/environments`) | T-27 | Bulk change | Several applications. | 1. Select more than one. 2. Apply a change to all of them. | Every selected application is changed; the others are untouched. | LOW |  |  | Not Run
USERS (`/users`) | T-28 | Create a user | An application exists. | 1. Press Create User. 2. Fill in name, email and extension number. 3. Save. 4. Open Devices. | The user is listed AND a device for them appears on Devices. | CRITICAL |  |  | Not Run
USERS (`/users`) | T-29 | The new user's phone can register | The user from T-28. needs: a softphone. | 1. Configure the softphone with that extension and its password. 2. Register it. 3. Open Devices. | The phone registers and the device shows as online. | CRITICAL |  |  | Not Run | A device that exists but was never sent to its node looks fine here and refuses every registration — this row is what catches that.
USERS (`/users`) | T-30 | The user can sign in to the portal | The user from T-28. | 1. Sign in at the user portal with their email and password. | They reach their own screens (My calls, Phone) and see only their own calls. | CRITICAL |  |  | Not Run
USERS (`/users`) | T-31 | Edit a user | The user from T-28. | 1. Change their name and save. 2. Reload. | The change is kept and shows on their device too. | MEDIUM |  |  | Not Run
USERS (`/users`) | T-32 | Import users from a file | A CSV of a few users. | 1. Press Import CSV. 2. Choose the file. 3. Import. | Every row in the file becomes a user, and the count matches. Bad rows are reported rather than silently skipped. | MEDIUM |  |  | Not Run
USERS (`/users`) | T-33 | Delete a user | The user from T-28. | 1. Delete them. 2. Open Devices. 3. Try to register their softphone. | The user and their device are gone and the phone can no longer register. | HIGH |  |  | Not Run
DEVICES (`/extensions`) | T-34 | Create a device | An application exists. | 1. Press Add Device. 2. Fill in Name, Device Number and SIP Password. 3. Save. | It appears in the list straight away. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-35 | The device registers | The device from T-34. needs: a softphone. | 1. Point the softphone at the platform with that number and password. 2. Register. 3. Reload the list. | The device shows as registered / online. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-36 | Call between two devices | Two registered devices. needs: two softphones. | 1. From device A, dial device B's number. | B rings, the call connects, both sides have audio, and hanging up ends it on both. | CRITICAL |  |  | Not Run
DEVICES (`/extensions`) | T-37 | Wrong password is refused | The device from T-34. | 1. Set the wrong SIP password on the softphone. 2. Register. | Registration is refused and the device stays offline. | HIGH |  |  | Not Run
DEVICES (`/extensions`) | T-38 | Edit a device | The device from T-34. | 1. Change its name and save. 2. Reload. | The change is kept. | MEDIUM |  |  | Not Run
DEVICES (`/extensions`) | T-39 | Change the SIP password | A registered device. | 1. Change its SIP password. 2. Re-register the softphone with the new one. | The new password works; the old one is refused. | MEDIUM |  |  | Not Run
DEVICES (`/extensions`) | T-40 | Import devices from a file | A CSV of a few devices. | 1. Press Import CSV. 2. Choose the file and import. | Every row becomes a device and the count matches. | MEDIUM |  |  | Not Run
DEVICES (`/extensions`) | T-41 | Filter the list | More than a page of devices. | 1. Use the filters and the search box. 2. Page through. | Results match what you asked for; paging does not lose or repeat rows. | LOW |  |  | Not Run
DEVICES (`/extensions`) | T-42 | Delete a device | The device from T-34. | 1. Delete it. 2. Try to register its softphone. | It is gone from the list and can no longer register. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-43 | Add a number | An application exists. | 1. Press Add DID. 2. Enter the number and save. | It is listed against that application. | CRITICAL |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-44 | A number rings a device | The number from T-43 and a registered device. needs: a way to dial the number. | 1. Point the number at that device. 2. Call the number from outside. | The device rings, the call connects with audio both ways. | CRITICAL |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-45 | A number goes to an IVR | An IVR with at least one option. | 1. Point the number at the IVR. 2. Call it. 3. Press the option. | You hear the menu and the key press takes you where the option says. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-46 | A number goes to a queue | A queue with an agent logged in. | 1. Point the number at the queue. 2. Call it. | You hear the queue treatment and the agent's phone rings. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-47 | Out-of-hours routing | A call condition for out of hours. | 1. Put a condition on the number so out of hours goes elsewhere. 2. Call it inside hours, then outside. | Each call lands where the condition says. | MEDIUM |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-48 | Copy a number's setup | A number that is fully set up. | 1. Press Duplicate DID. 2. Give it another number and save. | The copy has the same routing, with the new number. | LOW |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-49 | Import numbers from a file | A CSV of numbers. | 1. Import DIDs from CSV. | Every row becomes a number and the count matches. | MEDIUM |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-50 | Delete a number | The number from T-43. | 1. Delete it. 2. Call it. | It is gone from the list and the call is not answered by the platform. | HIGH |  |  | Not Run
ROUTING AND NUMBERS (`/routing`) | T-51 | Calling between two sites | needs: two PBXs / sites connected by a trunk rule. | 1. From a phone on site A, dial a site B extension. | The call reaches site B and connects. | MEDIUM |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-52 | Create a queue | A device to act as agent. | 1. Press Create Queue. 2. Add the device as an agent. 3. Save. | The queue is listed with its agent. | HIGH |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-53 | A queue call reaches the agent | The queue from T-52, agent registered. | 1. Call into the queue. | The agent's phone rings; answering connects the caller; the call appears in Calls. | HIGH |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-54 | Agent availability | The queue from T-52. | 1. Set the agent unavailable. 2. Call the queue. 3. Set them available and call again. | An unavailable agent is not rung; an available one is. | MEDIUM |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-55 | Create an IVR | An announcement to play. | 1. Press Create IVR. 2. Add a greeting and at least one key option. 3. Save. | The IVR is listed with its options. | HIGH |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-56 | Upload an announcement | An audio file. | 1. Press Create New Announcement. 2. Upload the file and save. 3. Play it back on the screen. | The recording is stored and plays back correctly. | MEDIUM |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-57 | Make an announcement from text | Text-to-speech configured. | 1. Open an announcement. 2. Type the words and press Generate Audio. 3. Play it back. | The spoken audio matches the text and is saved. | MEDIUM |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-58 | Create a call condition | An application exists. | 1. Press Create Call Condition. 2. Set a time range and a destination. 3. Save. | It is listed and can be picked when routing a number. | MEDIUM |  |  | Not Run
ROUTING RESOURCES — queues, IVRs, announcements, conditions | T-59 | Voicemail | A device with voicemail. | 1. Call it and leave a message when it goes unanswered. 2. Open the voicemail list. | The message is listed and plays back. | MEDIUM |  |  | Not Run
PROVIDERS (`/providers`) | T-60 | Add a provider | needs: carrier details. | 1. Press Add Provider. 2. Fill in the details and save. | It is listed. | HIGH |  |  | Not Run
PROVIDERS (`/providers`) | T-61 | Outbound call through the provider | The provider from T-60, a registered device. needs: a number you can call. | 1. Point outbound calls at the provider. 2. From the device, dial an outside number. | The far end rings, the call connects with audio, and it appears in Calls as outgoing. | CRITICAL |  |  | Not Run
PROVIDERS (`/providers`) | T-62 | Inbound from the provider | A number delivered by that provider. | 1. Call that number from outside. | The call arrives and follows the routing set for the number. | CRITICAL |  |  | Not Run
PROVIDERS (`/providers`) | T-63 | Edit a provider | The provider from T-60. | 1. Change a setting and save. 2. Reload. | The change is kept and calls still work. | MEDIUM |  |  | Not Run
PROVIDERS (`/providers`) | T-64 | Delete a provider | A provider not in use. | 1. Delete it. | It is gone from the list and from the routing choices. | MEDIUM |  |  | Not Run
NODES (`/nodes`) | T-65 | Which nodes are connected | You are signed in as root. | 1. Open Nodes. | Every node is listed with an up-to-date connected state, and the ones that are actually running show as connected. | CRITICAL |  |  | Not Run
NODES (`/nodes`) | T-66 | A node that is off shows as off | needs: a node you can stop. | 1. Stop the node. 2. Reload Nodes. | It shows as not connected within a few seconds, with a reason. | HIGH |  |  | Not Run
NODES (`/nodes`) | T-67 | A node's own health | A connected node. | 1. Open its health. | Its checks are listed; a node can be connected and still report a failing check. | MEDIUM |  |  | Not Run
NODES (`/nodes`) | T-68 | A node's logs | A connected node. | 1. Press its Logs button. | You see that node's own log lines, not the platform's. | MEDIUM |  |  | Not Run
NODES (`/nodes`) | T-69 | Add a node | You are root. | 1. Add a node and save. | It appears in the list. | MEDIUM |  |  | Not Run
NODES (`/nodes`) | T-70 | Only root sees Nodes | An account without node rights. | 1. Sign in as it. 2. Look for Nodes, then type the address directly. | The screen is neither listed nor reachable. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-71 | Start a call from the screen | A registered device. | 1. Start a call to that device from Calls. 2. Answer it. | The device rings, the call connects, and it appears in the live list while it runs. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-72 | A call in progress is shown | A call running. | 1. Watch the Calls screen while the call is up. | The call is listed with both parties and a running duration, and disappears when it ends. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-73 | The finished call is in the log | The call from T-71, hung up. | 1. Open the call log. | The call is there with the right numbers, direction, start time and duration. | CRITICAL |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-74 | End a call from the screen | A call running. | 1. Press hang up on that call. | Both phones drop within a second or two and the call leaves the live list. | HIGH |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-75 | Listen to a recording | A finished call that was recorded. | 1. Open it in the call log. 2. Play the recording. | It plays, and it is the right call. | MEDIUM |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-76 | Listen in on a call | A call running. needs: two devices plus your own. | 1. Use spy / listen on that call. | You hear both sides; the two parties do not hear you. | MEDIUM |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-77 | Pick up a ringing call | A device ringing. | 1. Use pickup from another device. | The ringing call is answered on your device and stops ringing on the first. | MEDIUM |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-78 | Filter and export the log | Several days of calls. | 1. Filter by date, direction and number. 2. Export. | The list matches the filter, and the export has the same rows. | MEDIUM |  |  | Not Run
CALLS (`/calls`, `/calls-log`) | T-79 | An agent sees only their own calls | A user with the portal. | 1. Sign in as the user. 2. Open My calls. | They see their own calls, and none of anyone else's. | CRITICAL |  |  | Not Run
MESSAGES (`/messages`) | T-80 | An incoming message arrives | needs: a messaging channel set up. | 1. Send a message to the platform number from outside. | It appears in Messages against the right conversation. | MEDIUM |  |  | Not Run
MESSAGES (`/messages`) | T-81 | Reply to a message | The conversation from T-80. | 1. Reply from the screen. | The reply reaches the sender and is shown in the thread. | MEDIUM |  |  | Not Run
CAMPAIGNS (`/campaigns`) | T-82 | Create a campaign | A number to call from. | 1. Create a campaign and add numbers to call. | It is listed with its numbers. | MEDIUM |  |  | Not Run
CAMPAIGNS (`/campaigns`) | T-83 | Run a campaign | The campaign from T-82. needs: a number you can answer. | 1. Start it. | The numbers are dialled, answered calls follow the campaign's flow, and each attempt shows in the call log. | MEDIUM |  |  | Not Run
CAMPAIGNS (`/campaigns`) | T-84 | Stop a campaign | A campaign running. | 1. Stop it. | No further numbers are dialled. | MEDIUM |  |  | Not Run
SERVICES (`/services`) | T-85 | Create a webhook | needs: a URL you can watch (any request-catching site). | 1. Press New Service. 2. Choose webhook, paste the URL, pick when it should fire and which applications it covers. 3. Save. | It is listed as enabled. | HIGH |  |  | Not Run
SERVICES (`/services`) | T-86 | The webhook is delivered | The service from T-85. **Wait one minute after saving.** | 1. Send it a test event with delivery turned on. 2. Look at your URL. 3. Open the service. | Your URL received the request, and the service's sent counter went up. | CRITICAL |  |  | Not Run | The screen reports that the event was *sent*, not that your endpoint accepted it — check your own endpoint and the counter. Changes take up to a minute to take effect; judging sooner makes a correct fix look broken.
SERVICES (`/services`) | T-87 | A real call fires it | The service from T-85, set to fire at end of call. | 1. Make and end a call on a covered application. 2. Look at your URL. | The request arrives for the real call, with that call's details. | HIGH |  |  | Not Run
SERVICES (`/services`) | T-88 | A disabled service does not fire | The service from T-85. | 1. Disable it. 2. Wait a minute. 3. Make a call. | Nothing is sent. | MEDIUM |  |  | Not Run
SERVICES (`/services`) | T-89 | It only covers its own applications | Two applications. | 1. Leave the service covering only application A. 2. Make a call on B, then on A. | Only the call on A is sent. | MEDIUM |  |  | Not Run
SERVICES (`/services`) | T-90 | Screen pop / CRM | needs: a CRM account. | 1. Set up the screen-pop service. 2. Take a call from a number known to the CRM. | The record opens for the agent. | MEDIUM |  |  | Not Run
SERVICES (`/services`) | T-91 | Delete a service | The service from T-85. | 1. Delete it. 2. Wait a minute and make a call. | It is gone from the list and nothing more is sent. | MEDIUM |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-92 | Add a subscription | An application. | 1. Press Add Subscription. 2. Pick the plan and dates. 3. Save. | It is listed against the application with its dates. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-93 | Edit a subscription | The subscription from T-92. | 1. Change it and save. 2. Reload. | The change is kept. | MEDIUM |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-94 | Add balance | The subscription from T-92. | 1. Press Add Balance and add an amount. | The balance goes up by that amount and a transaction is recorded. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-95 | Calls use the balance | A subscription with a small balance. needs: a chargeable call. | 1. Note the balance. 2. Make a chargeable call. 3. Reload. | The balance has gone down and the call is in Transactions with a cost. | CRITICAL |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-96 | No balance, no call | A subscription with no balance. | 1. Try a chargeable call. | The call is refused, and the reason is visible in Logs. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-97 | End a subscription | The subscription from T-92. | 1. Terminate it. 2. Try a chargeable call. | It shows as ended and chargeable calls stop working. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-98 | Create a tariff | You have full access. | 1. Press Create Tariff. 2. Add rates for a few prefixes, including one long and one short. | The tariff is listed with its rates. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-99 | What a number costs | The tariff from T-98, with rates for `1` and `1212`. | 1. Ask the tariff for the rate for a +1 212 number. | The more specific rate (`1212`) is the one quoted, not `1`. | HIGH |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-100 | A disabled rate is not used | The tariff from T-98. | 1. Disable one rate. 2. Ask for a number it covered. | That rate is no longer quoted. | MEDIUM |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-101 | Create a plan | A tariff. | 1. Create a plan and put the tariff on it. 2. Save. | It can be picked when adding a subscription. | MEDIUM |  |  | Not Run
SUBSCRIPTIONS, TARIFFS AND BILLING | T-102 | Transactions add up | A few charged calls. | 1. Open Transactions and compare with the call log for the same period. | The charges match the calls; nothing is missing or doubled. | MEDIUM |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-103 | Create a workflow | You have full access. | 1. Press New Workflow. 2. Build a small flow and save. | It is listed and can be reopened exactly as saved. | MEDIUM |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-104 | A workflow runs on a call | The workflow from T-103, attached to a call flow. | 1. Make a call that triggers it. 2. Open Events for that call. | The workflow's steps are recorded against the call. | MEDIUM |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-105 | Create a bot | needs: an AI provider configured. | 1. Press Create Bot. 2. Give it instructions and save. | It is listed. | MEDIUM |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-106 | A bot answers a call | The bot from T-105, pointed at a number. | 1. Call the number. 2. Speak to it. | It answers, responds sensibly, and the call is in the call log. | MEDIUM |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-107 | Create a schema | You have full access. | 1. Press New Schema. 2. Define it and save. | It is listed and reopens as saved. | LOW |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-108 | Create a template | You have full access. | 1. Create a template and save. 2. Use it somewhere it is offered. | It is offered and applies what it defines. | LOW |  |  | Not Run
AUTOMATION — workflows, bots, schemas, templates | T-109 | Ask the assistant | AI configured. | 1. Open the assistant and ask about your own data (for example how many calls today). | The answer matches what the screens show. | LOW |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-110 | Dashboard figures | Some calls today. | 1. Open the dashboard. 2. Compare with the call log for the same period. | The totals agree with the call log. | CRITICAL |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-111 | Live updates while a call runs | A registered device. | 1. Open the live screen. 2. Make a call and hang up. | The call appears while it runs and the counts go back down after it ends, without reloading. | CRITICAL |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-112 | Registered devices are counted | Two registered devices. | 1. Watch the live screen. 2. Unregister one. | The registered count falls by one. | MEDIUM |  |  | Not Run
DASHBOARD AND LIVE (`/`, `/live`) | T-113 | An empty period reads as empty | A quiet period. | 1. Open the charts for a period with no calls. | It says there is nothing, rather than showing an error or a blank box. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-114 | System health | You are signed in. | 1. Open the health screen. | Every check is listed and the essential ones are green. | CRITICAL |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-115 | A stopped service shows red | needs: a service you can stop. | 1. Stop it. 2. Reload health. | It goes red and names what is wrong. | HIGH |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-116 | Monitoring charts | Some traffic. | 1. Open Monitoring and pick a period. | Charts draw for that period and the periods agree with each other. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-117 | Alert thresholds | You have full access. | 1. Set a threshold low enough to trip. 2. Cause the condition. | An alert is raised and shown. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-118 | Recent activity in Logs | Anything done in the last few minutes. | 1. Open Logs. | Recent lines are there, newest first, with times that make sense. | HIGH |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-119 | Find a line | A call you just made. | 1. Search Logs for its number or reference. | The lines for that call are found. | HIGH |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-120 | Filter by app and severity | Some traffic. | 1. Filter to errors only, then to one app. | Only matching lines are listed. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-121 | A record's own history | Any device or number. | 1. Open it and press View Logs. | You see that record's lines and nothing unrelated. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-122 | A refused call is explained | needs: a number that is not configured. | 1. Call it. 2. Open Logs. | One line explains why the call was refused. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-123 | Events for a call | A finished call. | 1. Open Events and find it. | Its events are listed in order — ringing, answer, hangup. | MEDIUM |  |  | Not Run
MONITORING, HEALTH, LOGS AND EVENTS | T-124 | One customer's logs only | needs: a second customer. | 1. Sign in as customer A. 2. Search Logs for something of customer B's. | Nothing of customer B's is returned. | CRITICAL |  |  | Not Run
REPORTS AND NOTIFICATIONS | T-125 | Run a report | Some calls in the period. | 1. Open Reports, pick a period, run one. | The figures agree with the call log for that period. | HIGH |  |  | Not Run
REPORTS AND NOTIFICATIONS | T-126 | Export a report | The report from T-125. | 1. Export it. | The file downloads and has the same rows as the screen. | MEDIUM |  |  | Not Run
REPORTS AND NOTIFICATIONS | T-127 | Notifications | Something that raises one. | 1. Open Notifications. 2. Mark one as read. | It is listed, and it stays read after a reload. | LOW |  |  | Not Run
THE WHOLE WAY THROUGH — run this last | T-130 | A new customer, end to end | You are signed in with full access. needs: two softphones and a number. | 1. Create an application. 2. Create two users on it. 3. Register both softphones. 4. Add a number and point it at one of them. 5. Call between the two devices. 6. Call the number from outside. 7. Open the call log, the dashboard and Transactions. | Every step works without a developer touching anything, and the calls you made are the calls the log, the dashboard and the charges show. | CRITICAL |  |  | Not Run | If this row passes, the release is usable. If it fails, the release is not, whatever else passed.